## osri website redesign
OSRI Website Redesign
By Sakshi Verma
Planning
Name | Subitems | Due date | Status | Priority | Notes | Item ID (auto generated)
Call for Initial Redesign Concept Meeting |  | 2025-07-01 | Done | High | Prepared initial notes and ideas for redesign concept. | 9857020714
Create a PPT for Pitching the Idea |  | 2025-07-02 | Done | High | On shared OSR drive. | 9857622347
Present Idea to Dan |  | 2025-07-03 | Done | Medium | Pitched redesign idea to Dan | 9857020736
Approval to Proceed from Dan |  | 2025-07-04 | Done | Medium | Meeting Summary: Requested to not edit website content yet. Calander for AY 2025-26 not finalized yet. | 9857615959
Approval from Dr. K (Initial) |  | 2025-07-09 | Done | High | Secured approval from Dr. K to proceed | 9857020757
2025-07-01 to 2025-07-09
Requirements Gathering
Name | Subitems | Due date | Status | Priority | Notes | Item ID (auto generated)
Meeting with Dan (Expectations & Needs) |  | 2025-07-07 | Done | High | Got Dan's detailed expectations and suggestions | 9857020776
Compile Dan's Feedback |  | 2025-07-07 | Done | Medium | Converted Dan's suggestions into structured action items. | 9857020801
Coworker Meeting (A, C, & S) |  | 2025-07-08 | Done | Medium | Discussed student feedback trends and improvements. Notes attached. | 9857020824
Meeting with ITS Digital Transformation | Meet with Joe for Accessibility Reqs,Send Ray Images for the Tiles,Home PageEdits - ITS Permissions,Give OSR Button - Secure Permissions | 2025-07-12 | Done | High | Validated technical feasibility of redesign. | 9857020867
Subitems | Name | Status | Date | Timeline - Start | Timeline - End | Item ID (auto generated)
| Meet with Joe for Accessibility Reqs | Done | 2025-08-01 | 2025-07-28 | 2025-08-05 | 9875437001
| Send Ray Images for the Tiles | Done | 2025-08-15 |  |  | 9875435925
| Home PageEdits - ITS Permissions | Done | 2025-08-16 |  |  | 9875450832
| Give OSR Button - Secure Permissions |  | 2025-08-20 |  |  | 9875465558
Document Technical Requirements | Create a Figma account,Get Dan to put in the card for Figma | 2025-07-08 | Done | Medium | Created summary of ITS input and constraints. | 9857020882
Subitems | Name | Status | Date | Timeline - Start | Timeline - End | Item ID (auto generated)
| Create a Figma account | Done | 2025-07-05 |  |  | 9875420527
| Get Dan to put in the card for Figma | Done | 2025-07-08 |  |  | 9875421172
Coordinate with Visual Resource Center (VRC) |  | 2025-07-12 | Done | High | Email Sent. Requested banners and images for inclusivity. | 9857020904
Department & College Feedback |  | 2025-07-15 | Done | Medium | Collected ideas from websites from departments. | 9857020920
Research Other CSUSB Websites (JHBC, COE) |  | 2025-07-16 | Done | Medium | Analyzed best practices from colleges for inspiration. | 9857020937
Consult Office of Marketing & Communications |  | 2025-07-18 | Done | High | Aligned project with CSUSB branding & digital guidelines. | 9857020947
2025-07-07 to 2025-07-18
Proposal & Review
Name | Subitems | Due date | Status | Priority | Notes | Item ID (auto generated)
Draft Full Proposal | Renew Canva Subscription | 2025-07-23 | Done | High | Created full redesign proposal with visuals and timeline. | 9857020967
Subitems | Name | Status | Date | Timeline - Start | Timeline - End | Item ID (auto generated)
| Renew Canva Subscription | Done | 2025-08-12 |  |  | 9875430340
Review Proposal with Dan & Team |  | 2025-07-24 | Done | High | Gathered review comments and suggestions from team. | 9857020979
Revise Proposal with Feedback |  | 2025-07-25 | Done | High | Integrated Dan and teamâs feedback into final version. | 9857020994
Approval from Dr. K (Final) |  | 2025-07-27 | Done | High | Received final approval to implement redesign. | 9857021011
2025-07-23 to 2025-07-27
Design & Implementation
Name | Subitems | Due date | Status | Priority | Notes | Item ID (auto generated)
Design New Inclusive Banners |  | 2025-07-30 | Done | Medium | Created inclusive and visually strong banners. | 9857021026
Edit & Approve Banners |  | 2025-08-02 | Done | High | Revised designs and secured approvals. | 9857021040
Edit Website Content (UI/UX) | Get final AY 25 Calander,Secure New Grant Guidelines,Email Joe to Resize Tiles | 2025-08-07 | Done | High | Rewrote text for clarity and accessibility compliance. | 9857021066
Subitems | Name | Status | Date | Timeline - Start | Timeline - End | Item ID (auto generated)
| Get final AY 25 Calander | Done | 2025-08-08 | 2025-08-04 | 2025-08-09 | 9875446140
| Secure New Grant Guidelines | Done | 2025-08-08 | 2025-08-04 | 2025-08-08 | 9875447322
| Email Joe to Resize Tiles | Done | 2025-08-14 |  |  | 9875448257
Accessibility Review with Webservices |  | 2025-08-09 | Done | High | Reviewed site against accessibility standards. | 9857020720
Website Implementation ( New Content Upload) |  | 2025-08-15 | Done | High | Uploaded new content, menus, and layouts. | 9857020743
Internal Review - UI/UX & Functionaliy |  | 2025-08-18 | Done | High | Conducted end-to-end website testing. | 9857020765
Final Polishing & Adjustments |  | 2025-08-20 | Done | High | Minor adjustments before launch. | 9857020789
Website Launch (Go-Live) | Email Dr. K for Final Review/Suggestion | 2025-08-23 | Done | High | Delivered redesigned website before semester start! | 9857020809
Subitems | Name | Status | Date | Timeline - Start | Timeline - End | Item ID (auto generated)
| Email Dr. K for Final Review/Suggestion | Done | 2025-08-22 | 2025-08-19 | 2025-08-22 | 9875452229
2025-07-30 to 2025-08-23
Marketing Rollout
Name | Subitems | Due date | Status | Priority | Notes | Item ID (auto generated)
Draft Marketing & News Features |  | 2025-08-06 | Done | High | Prepared marketing content & rebranding stories. | 9857020831
Coordinate with Marketing Team for Rollout |  | 2025-07-30 | Done | Medium | Emailed Bri. | 9857020853
Publish Marketing Content (Web + Social) |  | 2025-08-29 | Done | High | Scheduled content to official channels via Meta. | 9857020872
Send Out Rebranding Email Communications |  | 2025-08-29 | Done | High | Sent out emails to attached colleges and departments to list OSRI as a resource on their website | 9867395992
Finalize Rebranding Campaign | Update Materials on Canva for Fall 2025 | 2025-08-30 | Done | High | Closed marketing cycle with successful rebranding launch. | 9857020889
Subitems | Name | Status | Date | Timeline - Start | Timeline - End | Item ID (auto generated)
| Update Materials on Canva for Fall 2025 | Done | 2025-08-30 | 2025-08-05 | 2025-08-30 | 9875459475
2025-07-30 to 2025-08-30

## osri website redesign-updates
OSRI Website Redesign | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
9857020714 | Call for Initial Redesign Concept Meeting | Update |  | Sakshi | 19/August/2025 09:24:17 PM | Prepared initial notes and ideas for redesign concept. Also create a PPT. | 0 |  | 4416621673
9857020714 | Call for Initial Redesign Concept Meeting | Update |  | Sakshi | 19/August/2025 09:25:57 PM | Book Meeting room for the meeting on July 3, 2025 | 0 |  | 4416622811
9857020882 | Document Technical Requirements | Update |  | Sakshi | 21/August/2025 08:02:53 PM | Link of files: | 0 |  | 4423561359
9857021040 | Edit & Approve Banners | Update |  | Sakshi | 21/August/2025 08:14:42 PM | Dan wanted the blue hues reduced | 0 |  | 4423569339
9857021040 | Edit & Approve Banners | Update |  | Sakshi | 21/August/2025 08:15:27 PM | Contact Corrine for photoshop guidance 8/6 | 0 |  | 4423570273
9857615959 | Approval to Proceed from Dan | Update |  | Sakshi | 21/August/2025 08:02:08 PM | Updated doc with Dani's comments is on Slack | 0 |  | 4423560795